## Slide 1: Project Planning and Communication Plans
Presenter: Jennifer LoGalbo
RHP 8 Monthly Learning Collaborative Call
January 13, 2015

## Slide 2: Objectives
Welcome and Introductions
Review Project Management Process
Define Planning Phase
Discuss Communication Plans
Share Resources/Examples
Q&A

## Slide 3: Project Management Process
Initiating
Monitoring
Closing
Planning
Executing
Select project manager
Define roles and responsibilities
Determine project team
Estimate costs and time
Complete the work
Report on performance
Measure performance against baseline
Update documents
Perform quality control
Divide large projects
Create objectives
Archive and index project documents
Gather lessons learned
Manage people
Create communication plan

## Slide 4: Planning Phase – 25 Steps
Planning (the only phase with a set order for processes – see complete list of 25 activities on slides 15-16)
Create project scope statement
Create procurement documents/assess what needs to be purchased
Create Work Breakdown Structure (WBS) and dictionary
Estimate resource requirements
Estimate time and costs
Decide on critical path
Create communication plan
Develop budget

## Slide 5: Planning Phase - Templates
Planning (the only phase with a set order for processes – see complete list of 25 activities on slides 15-16)
Create project scope statement
Create procurement documents/assess what needs to be purchased
Create Work Breakdown Structure (WBS) and dictionary
Estimate resource requirements
Estimate time and costs
Decide on critical path
Create communication plan
Develop budget
Total of 25 activities that should be addressed in this phase (see complete list on slide ##)

## Slide 6: What is a Communication Plan?
Purpose of the plan is to define the communication requirements for the project and how information will be distributed.
Defines communication channel with each stakeholder in order to determine preferred frequency and method of communication.
The plan lays the foundation for the communication framework and contains five major areas.

## Slide 7: Why are Communication Plans Important?
Communication consumes roughly 90% of a project manager’s time.
Many different communication methods, barriers, and technologies to navigate.
Remember, keep communications CLEAR!

## Slide 8: 1. Roles and Responsibilities
A well-managed project is best established when roles and responsibilities are clearly defined.
Make information easy-to-understand
Examples of roles and responsibilities to include:
  Project Sponsor(s), Project Manager, Project Team, and Stakeholders

## Slide 9: 2. Project Team Information
Also known as the “Project Team Directory”
Subject to change as project grows/shrinks
Keep updated and available for “worst case scenario”
Role | Name | Title | Organization/ Department | Email | Phone
Project Sponsor | Joe Smith | Executive Director | ABC Hospital | joe_smith@abchospital.waiver | 123-4567
Project Manager | Jane Doe | Project Manager II | ABC Hospital | jane_doe@abchospital.waiver | 123-8945
Project Team | Mike Smith | Marketing Director | ABC Hospital | mike_smith@abchospital.waiver | 123-6512
Stakeholder | Danny McDonald | County Judge | Healthy County | dm@healthycounty.waiver | 456-3258

## Slide 10: 3. Communication Matrix
Visually identifies communication requirements for the project.
Eight areas to include on the Matrix:
Communication Type | Objective of Communication | Medium | Frequency | Audience | Owner | Deliverable(s) | Location
Kickoff Meeting | Introduce the project team and the project. Review project objectives and management approach. | Face-to-Face | Once | Project Team | Project Manager | Agenda Meeting Minutes | All project documents are located on the internal share drive at this location: M:\projectfiles\patientnavigation\meetingminutes
Project Team Meetings | Review status of the project with the team. | Conference Call | Weekly | Project Team | Project Manager | Agenda Meeting Minutes Project schedule | 

## Slide 11: 4. Guidelines for Meetings
General rules meeting participants will adhere to during meetings related to the project.
Lists roles that may be assigned to various meeting participants at the meeting:
  Meeting Facilitator, Scribe: Meeting Minutes, Action Items, and Parking Lot, and Time Keeper
Any rules specific to your organization.

## Slide 12: 5. Glossary of Terms/Acronyms
Assume the person reading the communication plan is not familiar with the various terms used by the project team.
A glossary will help clear up any ambiguity of terms.

## Slide 13: Confidential Communications

## Slide 14: RACI Charts

## Slide 15: Planning Stage – Activities
Determine how you will plan for each knowledge area
Determine detailed requirements
Create project scope statement
Asses what to purchase and create procurement documents
Determine planning team
Create WBS and dictionary
Create activity list
Create network diagram
Estimate resource requirements
Estimate time and cost
Determine critical path
Develop schedule

## Slide 16: Planning Stage – Activities, Con’t.
Develop budget
Determine quality standards, processes, and metrics
Create process improvement plan
Determine all roles and responsibilities
Plan communications and stakeholder engagement
Preform risk identification, qualitative and quantitative risk analysis, and risk response planning
Go back – iterations
Finalize procurement documents
Create change management plan
Finalize the “how to execute and control” parts of all management plans
Develop realistic and final PM plan and performance measurement baseline
Gain formal approval of plan
Hold kickoff meeting

## Slide 17: Resources and Contact Information
Mulcahy, R. (2013). PMP exam prep: Accelerated learning to pass PMI's PMP exam (8th ed.). Minnetonka, Minn.: RMC publications.
Contact Information:
  Jennifer LoGalbo
  RHP 8 Program Director
  512-341-4962
  logalbo@tamhsc.edu

## Slide 18: Q&A